## TitlePhaseDateStatusDescription
ID | Title | Date/phase | Status | Description | Root Cause | Impact | Resolution | Key Files / Components Modified
1 | JTransform Library Missing | Early Dev | ✅ Resolved | The FFT library (JTransforms) needed for spectrogram generation was missing, causing runtime crashes. | Missing build.gradle.kts dependency declaration. | Critical - Complete failure of scream detection; app crashed. | Added the JTransforms dependency to the library's build file. | screamdetectionlibrary/build.gradle.kts
2 | Model Input Mismatch | TFLite Integration | ✅ Resolved | The model expected a 3-channel input [1,3,64,862] but was provided a single-channel input. | Misunderstanding of the model's architecture, which was trained on 3-channel inputs. | High - Incorrect/random confidence scores; accuracy was near zero. | Replicated the single-channel spectrogram across three channels before inference. | ScreamDetector.kt
3 | Missing Android Permissions | Service Impl. | ✅ Resolved | AndroidManifest.xml lacked critical permissions like RECORD_AUDIO and FOREGROUND_SERVICE. | Incomplete manifest configuration for a foreground service using the microphone. | Critical - Service crashed with SecurityException, microphone access denied. | Added all required permissions and the foregroundServiceType attribute. | AndroidManifest.xml, ScreamDetectionService.kt
4 | TFLite Model Not Loading | Asset Packaging | ✅ Resolved | The .tflite model file was not packaged into the AAR library, causing a FileNotFoundException. | Model file was not in the correct src/main/assets/ directory before building. | Critical - Complete failure of scream detection; service could not initialize. | Created the assets folder and placed the model file inside. | Project asset directory structure
5 | NNAPI Compatibility Issues | Performance Opt. | ✅ Resolved (Disabled) | Using NNAPI for hardware acceleration caused crashes and higher battery drain on some devices. | Buggy NNAPI drivers on certain devices and inefficient power usage. | High - Device-specific crashes, incorrect results, and 30-40% higher battery use. | Explicitly disabled NNAPI and GPU acceleration in TFLite options. | ScreamDetector.kt, DetectionConfig.kt
6 | Microphone Access Conflict | Keyword Detection | ✅ Resolved | AudioRecord and SpeechRecognizer tried to access the mic simultaneously. | Android OS disallows concurrent microphone access from two different sources. | Critical - Keyword detection was completely non-functional. | Replaced SpeechRecognizer with the Vosk library, which processes the same audio stream. | ScreamDetectionService.kt, VoskKeywordDetector.kt
7 | SpeechRecognizer Thread Violation | Keyword Detection | ✅ Resolved | SpeechRecognizer was called from a background thread instead of the required main (UI) thread. | Calling startListening() from a coroutine on the Dispatchers.IO context. | Medium - SpeechRecognizer failed to initialize, causing a silent failure. | Wrapped API calls in withContext(Dispatchers.Main). (Obsolete after Vosk). | ScreamDetectionService.kt
8 | Audio Threshold Too High | Initial Testing | ✅ Resolved | The initial decibel threshold of -25dB was too high, causing normal speech to be ignored. | Threshold was calibrated for loud screams only, not for conversational keywords. | High - Keyword detection was impossible unless the user shouted. | Lowered the threshold to -30dB to balance battery and sensitivity. | DetectionConfig.kt, ScreamDetector.kt
9 | Vosk Model Missing | Vosk Integration | ✅ Resolved | The Vosk language model was not packaged in the app's assets, causing initialization to fail. | Vosk models are large and require manual download and placement into assets. | Critical - Keyword detection was completely non-functional. | Added instructions and verification checks for manually placing the model. | VoskKeywordDetector.kt
10 | False Positives (Scream Only) | Production Test | ✅ Resolved | Alerting based on scream detection alone was triggered by loud noises like clapping or door slams. | Scream model's audio characteristics overlap with many non-distress sounds. | High - Eroded user trust due to excessive false alerts. | Enforced a strict mode requiring BOTH a scream and a keyword to be detected. | ScreamDetectionService.kt, DetectionConfig.kt
11 | Excessive Battery Drain | Production Deploy | ✅ Resolved | The service consumed 15-20% battery per hour, making it impractical for continuous use. | Continuous Vosk processing, large audio buffers, and low dB threshold. | Critical - The service was unusable for all-day background monitoring. | Implemented Vosk throttling, smaller buffers, and adaptive processing. | ScreamDetectionService.kt, DetectionConfig.kt
12 | Poor Hindi/Urdu Support | Battery Opt. | ✅ Resolved | The US English Vosk model had poor recognition accuracy for Hindi/Urdu keywords. | The acoustic model was not trained on Indian-subcontinent phonemes. | High - The system was ineffective for users in target regions. | Switched to the vosk-model-small-en-in-0.4 model. | DetectionConfig.kt, VoskKeywordDetector.kt
13 | High Detection Latency | Vosk Integration | ✅ Resolved | End-to-end detection latency was over 31 seconds, too slow for an emergency. | Large 10-second audio buffers with significant overlap and batch processing. | Critical - System was not practical for real-time distress detection. | Reduced buffer sizes and enabled real-time processing to lower latency to <15s. | DetectionConfig.kt, ScreamDetectionService.kt
14 | Consecutive Detection Logic | Fine-tuning | ⚙️ Configured | Requiring 2 consecutive detections adds a 2.5-5 second delay. | A deliberate trade-off to reduce false positives from isolated events. | Low - A slight, intentional increase in detection time. | Kept threshold at 2 for a balance of reliability and speed. | DetectionConfig.kt
15 | Alert Cooldown Period | Spam Prevention | ⚙️ Configured | A 5-second cooldown between alerts prevents spam but limits alert frequency. | A deliberate choice to prevent notification flooding and system overload. | Low - Only one alert is sent every 5 seconds during an ongoing event. | Kept at 5 seconds; the app should handle repeated alerts gracefully. | DetectionConfig.kt
16 | Centralized Configuration | Enhancement | ✅ Completed | Parameters were hardcoded across multiple files, making tuning difficult. | Lack of a single source of truth for system parameters. | Medium - Inefficient development workflow for tuning. | Created a DetectionConfig.kt object to centralize all parameters. | DetectionConfig.kt
17 | Battery Metrics Tracking | Enhancement | ✅ Completed | No way to quantitatively measure the impact of battery optimizations. | Lack of instrumentation for performance and power usage. | Medium - Difficult to validate if changes were effective. | Implemented tracking and broadcasting for key metrics (e.g., Vosk throttle rate). | ScreamDetectionService.kt
18 | False Positives (Keyword Only) | Strict Mode Impl. | ✅ Completed | Allowing alerts on keywords alone caused false positives from TV or conversations. | Distress keywords are common in media and everyday speech. | High - Caused 60-70% of false positives from background speech. | Removed the keyword-only detection path entirely. | ScreamDetectionService.kt
19 | Emergency Screen Not Reopening | testing | ✅ Resolved | The emergency screen didn't reappear on subsequent detections after the first one. | React Native navigation only works when the app is active; no global service existed. | Critical - Multiple detections failed, making the system unreliable. | Created a global NavigationService and added a timestamp prop to force new instances. | src/utils/NavigationService.js, App.jsx
20 | Emergency Screen Not Generic | testing | ✅ Resolved | The emergency screen was hardcoded for voice detection and couldn't be used for other triggers. | Initial design assumed only voice triggers; no flexible data structure was used. | High - Other developers couldn't reuse the screen for different triggers. | Refactored the screen to accept generic triggerType and triggerData props. | src/screens/EmergencyScreen.jsx
21 | State Persistence Issue | testing | ✅ Resolved | On app reopen, the UI toggle showed OFF even if the detection service was still running. | React state is lost on app closure; no sync with the native service status. | High - Caused user confusion and displayed an inaccurate UI state. | Used AsyncStorage for state persistence and synced the UI with native status on startup. | src/screens/ModifyTriggers.jsx, VoiceDetectionModule.kt
22 | Unwanted Navigation on Toggle | testing | ✅ Resolved | Clicking the voice trigger card navigated to a non-existent VoiceSettingsScreen. | The card's onPress handler was incorrectly configured for the voice trigger. | Low - Unwanted navigation but did not break core functionality. | Disabled the onPress navigation for the voice trigger card. | src/screens/ModifyTriggers.jsx
23 | Screen Not Opening From Lock | testing | ✅ Resolved | The emergency screen failed to open when the device screen was off or locked. | No mechanism to wake the device and bring the app to the foreground from a killed state. | Critical - The system failed in most real-world scenarios (e.g., phone in pocket). | Added a native wake-up system using a wake lock and full-screen intent notification. | VoiceDetectionModule.kt, AndroidManifest.xml
24 | Kotlin Compilation Error | testing | ✅ Resolved | Build failed with "Unresolved reference" for FLAG_ACTIVITY_SHOW_WHEN_LOCKED. | These flags are not directly accessible in the Intent class in newer Android versions. | High - The app would not build, blocking all testing. | Used the direct hex values for the flags (0x00080000, 0x00200000). | VoiceDetectionModule.kt
25 | React Navigation setState Error | testing | ✅ Resolved | Console error: "Cannot update a component while rendering a different component." | Navigation was called synchronously during an event listener callback. | Medium - Caused error logs and potential navigation issues. | Wrapped the Maps() call in a setTimeout to defer it to the next render tick. | src/services/VoiceDetectionService.js
26 | Background Activity Start Blocked | testing | ✅ Resolved | Android 10+ security restrictions blocked the app from starting an activity from the background. | The system logcat showed "allowBackgroundActivityStart: false". | Critical - The app would not launch from the background or when the screen was off. | Implemented a full-screen intent notification, the correct Android method for this use case. | VoiceDetectionModule.kt
27 | NativeEventEmitter Warnings | testing | ⚠️ Warning Only | Console warnings about NativeEventEmitter missing addListener method. | The native module doesn't implement optional listener methods. | Low - The warnings are cosmetic and do not affect functionality. | No fix was needed as the module works correctly; the warnings can be safely ignored. | src/services/VoiceDetectionService.js
28 | Unresolved reference 'EmergencyAccessibilityService' | Build Error | ✅ FIXED | Kotlin compiler couldn't find EmergencyAccessibilityService class after deletion. | Service file was deleted but references remained in VoiceDetectionModule.kt. | High - Build failed with compilation error. | Removed isAccessibilityServiceEnabled() method and all service imports. | VoiceDetectionModule.kt (line 386)
29 | Missing OverlayPermissionManager implementation | Runtime Error | ✅ FIXED | OverlayPermissionManager.js file was created but left empty. | File was created but not populated with code. | Medium - Settings wouldn't open when toggling voice detection. | Filled OverlayPermissionManager.js with complete permission checking logic. | OverlayPermissionManager.js
30 | Accessibility card still showing in UI | UI Issue | ✅ FIXED | Accessibility Service card/banner was still displayed on ModifyTriggers screen. | Old accessibility code wasn't removed from JSX. | Low - Confusing user experience with outdated permission request. | Removed entire accessibility card component from ModifyTriggers.jsx. | ModifyTriggers.jsx (lines 399-461)
31 | checkAccessibilityStatus() function still called | Runtime Error | ✅ FIXED | AppState listener was calling the removed accessibility check function. | Function was deleted but still referenced in useEffect. | High - App would crash when coming to the foreground. | Removed AppState listener and checkAccessibilityStatus function call. | ModifyTriggers.jsx (lines 84-94)
32 | accessibilityEnabled state variable unused | Code Issue | ✅ FIXED | State variable was declared but no longer used after removing the accessibility card. | Leftover code from the previous implementation. | Low - Unnecessary state management. | Removed the accessibilityEnabled state variable. | ModifyTriggers.jsx (line 70)
33 | BIND_ACCESSIBILITY_SERVICE permission declared | Manifest Error | ✅ FIXED | The accessibility permission was still in AndroidManifest.xml. | Permission wasn't removed when the service was deleted. | Low - App requests an unnecessary permission. | Removed BIND_ACCESSIBILITY_SERVICE permission from the manifest. | AndroidManifest.xml
34 | EmergencyAccessibilityService still in manifest | Manifest Error | ✅ FIXED | The service declaration was still in AndroidManifest.xml. | Service component wasn't removed from the manifest. | Low - Manifest references a non-existent service. | Removed the entire <service> declaration for EmergencyAccessibilityService. | AndroidManifest.xml
35 | SYSTEM_ALERT_WINDOW permission missing | Permission Error | ✅ FIXED | The new overlay permission wasn't added to the manifest. | Forgot to add the replacement permission for the overlay. | Critical - Emergency screen couldn't display over other apps. | Added <uses-permission ... SYSTEM_ALERT_WINDOW" /> to the manifest. | AndroidManifest.xml
36 | openSystemAlertWindowSettings() method missing | Native Module Error | ✅ FIXED | VoiceDetectionModule.kt didn't have a method to open overlay settings. | The method wasn't implemented in the native bridge. | Medium - Settings couldn't be opened from React Native. | Added openSystemAlertWindowSettings() method to VoiceDetectionModule.kt. | VoiceDetectionModule.kt (lines 284-301)
37 | Overlay permission check missing | Permission Check Error | ✅ FIXED | checkAllPermissions() wasn't checking the overlay permission status. | The permission check logic was incomplete. | Medium - Couldn't verify if the overlay permission was granted. | Added systemAlertWindow check in checkAllPermissions() method. | VoiceDetectionModule.kt (lines 210-221)
38 | Accessibility broadcast still in ScreamDetectionService | Service Logic Error | ✅ FIXED | A 4th broadcast method was still sending to the accessibility service. | The old multi-broadcast system wasn't updated. | Low - Wasted resources on a non-existent service. | Removed the com.ui.ACCESSIBILITY_EMERGENCY broadcast. | ScreamDetectionService.kt (lines 593-661)
39 | No automatic settings opening on voice toggle | UX Issue | ✅ FIXED | The voice detection toggle didn't automatically open overlay settings. | The code was present but OverlayPermissionManager was empty. | Medium - User had to manually navigate to settings. | Populated OverlayPermissionManager and integrated it into the toggle flow. | ModifyTriggers.jsx, OverlayPermissionManager.js