## Sheet1
ID | Title | Status | Description | Root Cause | Impact | Resolution | Key Files / Components Modified
1 | JTransform Library Missing | Fixed | The FFT library (JTransforms) needed for spectrogram generation was missing, causing runtime crashes. | Missing build.gradle.kts dependency declaration. | Complete failure of scream detection; app crashed during audio processing. | Added the JTransforms dependency to the library's build file. | screamdetectionlibrary/build.gradle.kts
2 | Model Input Mismatch | Fixed | The model expected a 3-channel input [1,3,64,862] but was provided a single-channel input. | Misunderstanding of the model's architecture, which was trained on 3-channel inputs. | Incorrect/random confidence scores; detection accuracy was near zero. | Modified code to replicate the single-channel spectrogram across three channels before inference. | ScreamDetector.kt
3 | Missing Android Permissions | Fixed | The AndroidManifest.xml lacked critical permissions like RECORD_AUDIO and FOREGROUND_SERVICE. | Incomplete manifest configuration for a foreground service that uses the microphone. | Service crashed with SecurityException, microphone access was denied, and the system killed the service. | Added all required permissions and the foregroundServiceType attribute to the manifest. | AndroidManifest.xml, ScreamDetectionService.kt
4 | TFLite Model Not Loading | Fixed | The .tflite model file was not packaged into the AAR library, causing a FileNotFoundException. | The model file was not placed in the correct src/main/assets/ directory before building. | Complete failure of scream detection; service could not initialize. | Created the assets folder in the library module and placed the model file inside. | Project asset directory structure
5 | NNAPI Compatibility Issues | Fixed (Disabled) | Using the NNAPI for hardware acceleration caused crashes and higher battery drain on some devices. | Buggy NNAPI drivers on certain devices and inefficient power usage compared to CPU. | Device-specific crashes, incorrect results, and 30-40% higher battery consumption. | Explicitly disabled NNAPI and GPU acceleration in the TFLite interpreter options. | ScreamDetector.kt, DetectionConfig.kt
6 | Microphone Access Conflict | Fixed | AudioRecord (for scream detection) and SpeechRecognizer (for keywords) tried to access the mic simultaneously. | Android OS does not allow concurrent microphone access from two different sources. | Keyword detection was completely non-functional, logging ERROR_NO_MATCH. | Replaced SpeechRecognizer with the Vosk library, which processes the same audio stream from AudioRecord. | ScreamDetectionService.kt, VoskKeywordDetector.kt
7 | SpeechRecognizer Thread Violation | Fixed | The SpeechRecognizer API was called from a background thread instead of the required main (UI) thread. | Calling startListening() from a coroutine on the Dispatchers.IO context. | SpeechRecognizer failed to initialize, causing a silent failure of keyword detection. | Wrapped the API calls in withContext(Dispatchers.Main) to switch to the main thread. (Obsolete after Vosk). | ScreamDetectionService.kt
8 | Audio Threshold Too High | Fixed | The initial decibel threshold of -25dB was too high, causing normal speech (including keywords) to be ignored. | The threshold was calibrated for loud screams only, not for conversational-level keywords. | Keyword detection was impossible unless the user shouted. | Lowered the threshold to -30dB to balance battery life and sensitivity to normal speech. | DetectionConfig.kt, ScreamDetector.kt
9 | Vosk Model Missing | Fixed | The Vosk language model was not packaged in the app's assets, causing initialization to fail. | Vosk models are large and require manual download and placement into the assets folder. | Keyword detection was completely non-functional; Vosk failed to initialize. | Added instructions and verification checks for manually placing the model in the library's assets. | VoskKeywordDetector.kt, ADD_VOSK_MODEL.md
10 | False Positives (Scream Only) | Fixed | Alerting based on scream detection alone (>0.7 confidence) was triggered by loud noises like clapping or door slams. | The scream model's audio characteristics overlap with many common high-amplitude, non-distress sounds. | Eroded user trust due to excessive false alerts, leading users to disable the service. | Enforced a strict mode requiring BOTH a scream and a keyword to be detected together. | ScreamDetectionService.kt, DetectionConfig.kt
11 | Excessive Battery Drain | Fixed | The initial implementation consumed 15-20% battery per hour, making it impractical for continuous use. | Continuous Vosk processing, large audio buffers, low dB threshold, and high thread count. | The service was unusable for all-day background monitoring. | Implemented comprehensive optimizations: Vosk throttling, smaller buffers, higher dB threshold, and adaptive processing. | ScreamDetectionService.kt, DetectionConfig.kt
12 | Poor Hindi/Urdu Support | Fixed | The initial US English Vosk model had poor recognition accuracy for Hindi/Urdu distress keywords. | The acoustic model was not trained on Indian-subcontinent phonemes and accents. | The system was ineffective for users in target regions like India and Pakistan. | Switched to the vosk-model-small-en-in-0.4 model, which is smaller and optimized for Indian English. | DetectionConfig.kt, VoskKeywordDetector.kt
13 | High Detection Latency | Fixed | The end-to-end detection latency was over 31 seconds, which is too slow for an emergency response. | Large 10-second audio buffers with significant overlap and delayed batch processing of audio. | The system was not practical for real-time distress detection. | Reduced buffer sizes and overlap, enabling real-time processing and reducing latency to <15 seconds. | DetectionConfig.kt, ScreamDetectionService.kt
14 | Consecutive Detection Logic | Configured | The requirement for 2 consecutive detections adds a 2.5-5 second delay. | This is a deliberate trade-off to reduce false positives from brief, isolated events. | A slight increase in detection time. | Kept the threshold at 2 as a balance between reliability (<5% false positive rate) and speed. | DetectionConfig.kt
15 | Alert Cooldown Period | Configured | A 5-second cooldown between alerts prevents spam but limits alert frequency in a continuous event. | This is a deliberate design choice to prevent notification flooding and system overload. | Only one alert is sent every 5 seconds during an ongoing distress event. | Kept at 5 seconds, as the consuming app should handle repeated alerts gracefully. | DetectionConfig.kt
16 | Centralized Configuration | Completed | Parameters were hardcoded across multiple files, making tuning difficult and error-prone. | Lack of a single source of truth for system parameters. | Inefficient development workflow for tuning and optimization. | Created a DetectionConfig.kt object to centralize all configurable parameters. | DetectionConfig.kt
17 | Battery Metrics Tracking | Completed | There was no way to quantitatively measure the impact of battery optimizations. | Lack of instrumentation for performance and power usage. | Difficult to validate if battery-saving changes were effective. | Implemented tracking for key metrics (e.g., Vosk throttle rate, uptime) and broadcast them. | ScreamDetectionService.kt
18 | False Positives (Keyword Only) | Completed | Allowing alerts based on keywords alone caused false positives from TV, radio, or background conversations. | Distress keywords are common in media and everyday speech. | 60-70% of false positives were from background speech/media. | Removed the keyword-only detection path entirely; alerts now require a scream. | ScreamDetectionService.kt
19 | State Persistence Issue | Completed | On app reopen, the UI toggle showed OFF even if the detection service was still running. | React state is lost on app closure; no sync with the native service status. | High - Caused user confusion and displayed an inaccurate UI state. | Used AsyncStorage for state persistence and synced the UI with native status on startup. | src/screens/ModifyTriggers.jsx, VoiceDetectionModule.kt
20 | Unwanted Navigation on Toggle | Completed | Clicking the voice trigger card navigated to a non-existent VoiceSettingsScreen. | The card's onPress handler was incorrectly configured for the voice trigger. | Low - Unwanted navigation but did not break core functionality. | Disabled the onPress navigation for the voice trigger card. | src/screens/ModifyTriggers.jsx
21 | Kotlin Compilation Error | Completed | Build failed with "Unresolved reference" for FLAG_ACTIVITY_SHOW_WHEN_LOCKED. | These flags are not directly accessible in the Intent class in newer Android versions. | High - The app would not build, blocking all testing. | Used the direct hex values for the flags (0x00080000, 0x00200000). | VoiceDetectionModule.kt
22 | React Navigation setState Error | Completed | Console error: "Cannot update a component while rendering a different component." | Navigation was called synchronously during an event listener callback. | Medium - Caused error logs and potential navigation issues. | Wrapped the Maps() call in a setTimeout to defer it to the next render tick. | src/services/VoiceDetectionService.js
23 | NativeEventEmitter Warnings | Warning Only | Console warnings about NativeEventEmitter missing addListener method. | The native module doesn't implement optional listener methods. | Low - The warnings are cosmetic and do not affect functionality. | No fix was needed as the module works correctly; the warnings can be safely ignored. | src/services/VoiceDetectionService.js